## Question 2
Responsibility Assignment Matrix (RAM)
Key: P= Primary Responsibility S=Support Responsibility

## Question 4
Activity | ES | EF | Estimated Duration | LS | LF | Slack
Select Layout | 0 | 10 | 10 | 0 | 10 | 0
Design Graphics | 10 | 30 | 20 | 15 | 35 | 5
Approve Design | 30 | 60 | 30 | 35 | 65 | 5
Write Content | 60 | 75 | 15 | 60 | 75 | 0
Approve Content | 75 | 95 | 20 | 75 | 95 | 0
Insert Content into Page | 95 | 105 | 10 | 100 | 110 | 5
Set up Test Web Service | 105 | 125 | 20 | 110 | 130 | 5
Perform Tests | 125 | 140 | 15 | 135 | 150 | 10
Approve Web Service | 140 | 150 | 10 | 145 | 155 | 5
Go Live | 150 | 155 | 5 | 150 | 155 | 0

## Question 5
Position | June | July | August | September | October | November | Total | Cumulative Total
System Engineer II | 10000 | 12000 | 8000 | 10500 | 9000 | 11500 | 61000 | 61000
Software Engineer III | 8500 | 9500 | 9000 | 8000 | 9500 | 9000 | 53500 | 114500
Lead System Engineer | 6000 | 6500 | 7000 | 6500 | 7500 | 6000 | 39500 | 154000
Quality Engineer II | 5500 | 5000 | 4500 | 6000 | 5500 | 4500 | 31000 | 185000
Project Manager | 15000 | 20000 | 18000 | 15000 | 19000 | 16000 | 103000 | 288000
Chief Engineer | 12000 | 14000 | 12000 | 11000 | 13000 | 11500 | 73500 | 361500
Overhead | 10838 | 13091 | 8866 | 11576 | 9909 | 12650 | 66930 | 428430
Total Cost | 68838 | 80091 | 67366 | 68576 | 74409 | 71150 | 428930
Activity | June | July | August | September | October | November | Total | Cumulative Total
Select Layout | 2000 | 1500 | 0 | 0 | 0 | 0 | 3500 | 3500
Design Graphic | 5000 | 4500 | 3000 | 0 | 0 | 0 | 12500 | 16000
Approve Design | 0 | 1000 | 1500 | 0 | 0 | 0 | 2500 | 18500
Write Content | 0 | 3000 | 2500 | 0 | 0 | 0 | 5500 | 24000
Insert Content into Page | 0 | 0 | 2000 | 1500 | 0 | 0 | 3500 | 27500
Set Up Test Web Service | 0 | 0 | 0 | 3000 | 2500 | 0 | 5500 | 33000
Perform Tests | 0 | 0 | 0 | 2500 | 2000 | 1500 | 6000 | 39000
Approve Web Cost | 0 | 0 | 0 | 0 | 1500 | 2000 | 3500 | 42500
Go Live | 0 | 0 | 0 | 0 |  | 3000 | 3000 | 45500
Overhead | 1241 | 1774 | 1598 | 1241 | 1065 | 1152 | 8071
Total Budgeted Cost | 8241 | 11774 | 10598 | 8241 | 7065 | 7652 | 53571